## AHJ Meeting Agenda

Project - Nebius Data Center Building #1

Independence, MO 64056

ARCO Job No. MCI100

Meeting Date: 03/10/2026

- Attendees and Introductions:

| Name | Title | Company | Email | Phone | Present |
| --- | --- | --- | --- | --- | --- |
| Tom Scannell | Community Development Director | City of Independence | tscannell@indepmo.org | (816) 325-7830 |  |
| Charlie Dissell | Assistant City Manager | City of Independence | cdissell@indepmo.org | (816)-325-7987 |  |
| JC Farris | Commercial Plans Examiner | City of Independence | jfarris@indepmo.org | (816)-325-7401 |  |
| Brad Phelps | Flood plain development | City of independence | bpelphs@indepmo.org | (816) 325-7171 |  |
| Kris McGinley | Senior District Planner - IPL | City of Independence | kmcginley@indepmo.org |  |  |
| Steve Engelke | Engineering Technician Supervisor - Water | City of Independence | sengelke@indepmo.org | (816) 325-7711 |  |
| James Walton | Sanitary District | City of Independence | jwalton@indepmo.org | (816) 325-7600 |  |
| Aaron Spirek | Vice President & Operating Partner | ARCO | aspirek@arco1.com | (314) 443-4144 |  |
| Ryan Halley | Project Manager | ARCO | rhalley@arco1.com | (314) 225-0461 |  |
| Evan Evans | Superintendent | ARCO | eevans@arco1.com | (314) 227-6266 |  |
| Tom Rose | Superintendent | ARCO | trose@arco1.com | (314) 598-3099 |  |
| Nate Hoel | Superintendent | ARCO | nhoel@arco1.com | 557-232-7073 |  |
| Ryan Jobe | Superintendent | ARCO | rjobe@arco1.com |  |  |

- AHJ & Associated Departments Contract Information:

  - Building Department:

    - Contact Information for scheduling inspections

      - Name:

      - P: (816) 325-7401

      - E: bpermits@indepmo.org

    - Inspector(s) contact information

      - Name:

      - P:

      - E:

  - Plan Review Department - Onsite Improvements:

    - Contact Information:

      - Name:

      - P: (816) 325-7401

      - E: bpermits@indepmo.org

  - Public Work Department - Offsite Improvements:

    - Contact Information:

      - Name

      - P:

      - E:

  - Fire Department:

    - Fire Chief Contact Information

      - Name:

      - P:

      - E:

    - Fire Marshal Contact Information

      - Name:

      - P:

      - E:

    - Fire Department Plan Reviewer Contact Information

      - Name:

      - P:

      - E:

  - Health Department:

    - Plan Reviewer Contact Information

      - Name:

      - P:

      - E:

    - Inspector Contact Information

      - Name:

      - P:

      - E:

  - Water Department

    - Plan Reviewer Contact Information

      - Name:

      - P:

      - E:

    - Inspector Contact Information

      - Name:

      - P:

      - E:

  - Sewer (LBVSD):

    - Plan Reviewer Contact Information

      - Name:

      - P:

      - E:

    - Inspector Contact Information

      - Name:

      - P:

      - E:

  - Erosion Control:

    - Plan Reviewer Contact Information

      - Name:

      - P:

      - E:

    - Inspector Contact Information

      - Name:

      - P:

  - MODot:

    - Plan Reviewer Contact Information

      - Name:

      - P:

      - E:

    - Inspector Contact Information

      - Name:

      - P:

      - E:

  - IPL:

    - Plan Reviewer Contact Information

      - Name:

      - P:

      - E:

    - Inspector Contact Information

      - Name:

      - P:

      - E:

  - Any other team members?

    - Fiber / Internet service provider?

      - Who is the local provider?

    - Planning Inspections?

    - Landscaping Inspector?

  - Are there any local community organizations that may have input on this project?

- Design Considerations

  - Building appearance and exterior skin type

  - Mitigate sound/light

- Anticipated Permit Submission/Approval Schedule

  - Ground Improvement Permit

    - Submission Date: 4/17/2026

    - Duration for review comments: 10 Days

    - Receive Permit: 10 Days

  - Earthwork Permit

    - Submission Date: 4/17/2026

    - Duration for review comments: 10 Days

    - Receive Permit: 10 Days

  - Foundation Permit

    - Submission Date: 04/17/2026

    - Duration for review comments: 10 Days

    - Receive Permit: 10 Days

  - Underground Utilities Permit

    - Submission Date: 04/17/2026

    - Duration for review comments: 10 Days

    - Receive Permit: 10 Days

  - Superstructure/Shell Permit (div. 3, 5, 7)

    - Submission Date: 05/14/2026

    - Duration for review comments: 10 Days

    - Receive Permit: 10 Days

  - Interior Finishes Permit

    - Submission Date: 05/14/26

    - Duration for review comments: 10 Days

    - Receive Permit: 10 Days

  - Landscaping Permit

    - Submission Date: 05/14/26

    - Duration for review comments: 10 Days

    - Receive Permit: 10 Days

  - Site Improvements/Core/Shell/Systems Permit (Includes MEPFP)

    - Submission Date: 06/19/2026

    - Duration for review comments: 10 Days

    - Receive Permit: 10 Days

  - Any other misc. permits that may be required?

    - Construction Trailer Permit or entrance?

    - Fence Permit?

    - Temporary Shelters Permit?

    - Temporary Utilities? (power, water, etc.)

      - Two water & two power temp meters – what is the process?

        - One meter off 78 and Bly rd. & one meter north side of Bly rd. near pump station.

      - Lead time on temp power meter

        - Power restrictions/how much can we use on a temp service?

      - Lead time on temp water meter?

        - Sizes for temp water meter?

      - Sanitary tie-in to LBVSD manhole (may need to raise MHs onsite) east of Bly near pump station

    - Erosion Control Permit process?

    - Tree Clearing Permit process?

    - Engineering Permit?

- Permitting Procedures

  - How do the plans get submitted, and who reviews which set?

  - Do all disciplines (Civil, Architectural, Structural, MEP, and Fire Protection) get submitted to the Building Dept. and then distributed to the different reviewers internal? or do we do submit to different reviewing departments?

  - Does the Fire Dept., review the egress/lighting/truck routes/turn lane plans in addition to Fire Protection Plans?

    - If so, does the Fire Dept. review them concurrently with the Building Dept.?

  - How many sets of plans get submitted to the reviewing parties?  Full size? Is electronic seal allowed?  Do the plans need to be sealed when they are submitted for plan check, or only the set that the permit gets issued off of needs to be sealed?

  - How would you like the sets bound?  All together? By trade?

  - Does the Building Permit cover all trades or do the plans get approved and the various trades have to pull the individual permit (mechanical, plumbing, etc.)?

  - What review and approval needs to be completed before the permits are issued (e.g. Planning and Fire have to approve the plans before the Building Dept. can issue the Building Permit)

  - What is the standard review time duration? Are there different review times for different permit packages? Expedited duration/fee?

  - Are there any options to expedite the review or break up permits (grading, foundations, underground, etc.)?

  - Is there a backlog?  Can an SD set be submitted and then swapped prior to the actual review?

  - What is the second review time duration? Can the secondary review be expedited? IF so, duration/fee?

  - Building permit application form location?

  - Any other Forms needed, and where can we access them?

  - Fee schedules?

  - Any upfront fees?

  - Discuss temporary structures on site prior to grading or building permit approvals. Are temporary structures allowed in easements?

    - Trailers

- Inspections

  - Building Inspection process

- Building Inspector(s)

      - Is the Building Inspector a combined inspector?

      - Building, Mechanical, Plumbing, and Electrical?

      - How are inspections recorded?

      - Is there an inspection card?

      - Is there a list of what needs to be inspected?

      - Any requirements prior to starting building construction?

      - Inspection schedule?

        - What is the timeline for inspections?

        - Is there a deadline for inspections? Example: Must call in an inspection by 5:00 pm EST the day before.

        - Is there an online inspection service?

    - 3rd Party inspection?

    - Any other requirements?

  - Fire Inspection

- Fire Inspector(s)

      - Is the fire Inspector a combined inspector?

      - Sprinklers, fire alarm, underground, etc.?

        - Does the Fire Alarm have to have a wireless connection or a hard line?

      - How are inspections recorded?

      - Is there an inspection card?

      - Is there a list of what needs to be inspected?

      - Any requirements prior to starting building construction?

      - Inspection schedule?

        - What is the timeline for inspections?

        - Is there a deadline for inspections? Example:  Must call in an inspection by 5:00 pm EST the day before.

        - Is there an online inspection service?

    - 3rd Party inspection?

    - Any other requirements?

  - Health Inspections

- Health Inspector(s)

      - Is there a list of what needs to be inspected?

        - Percolation Test?

      - How are inspections recorded?

      - Is there an inspection card?

      - Is there a list of what needs to be inspected?

      - Any requirements prior to starting building construction?

      - Inspection schedule?

        - What is the timeline for inspections?

        - Is there a deadline for inspections? Example:  Must call in an inspection by 5:00 pm EST the day before.

        - Is there an online inspection service?

    - 3rd Party inspection?

    - Any other requirements?

  - Water and Sewer Dept. Inspections

- Water and Sewer Inspector(s)

      - Is there a list of what needs to be inspected?

      - How are inspections recorded?

      - Is there an inspection card?

      - Is there a list of what needs to be inspected?

      - Any requirements prior to starting building construction?

      - Inspection schedule?

        - What is the timeline for inspections?

        - Is there a deadline for inspections? Example:  Must call in an inspection by 5:00 pm EST the day before.

        - Is there an online inspection service?

    - 3rd Party inspection?

    - Any other requirements?

  - Erosion Control Inspections

- Erosion Control Inspector(s)

      - Is there a list of what needs to be inspected?

        - Percolation Test?

      - How are inspections recorded?

      - Is there an inspection card?

      - Is there a list of what needs to be inspected?

      - Any requirements prior to starting building construction?

      - Inspection schedule?

        - What is the timeline for inspections?

        - Is there a deadline for inspections? Example:  Must call in an inspection by 5:00 pm EST the day before.

        - Is there an online inspection service?

    - 3rd Party inspection?

    - Any other requirements?

- Administrative & Compliance Requirements

  - Design change process?

  - As-Builts process?

  - Bond requirements?

  - Any Impact/Capacity Fees?

- Miscellaneous

  - Work Hours?

  - Noise/lighting Restrictions?

  - Complaint issues?

  - Traffic Restrictions?

- Questions